SUN CSA Advocacy Plan 2023

Current Join Topics

- First 1000 Days of Life

- Inclusion of vulnerable people, including ethnic minorities, PWDs, people living with illness, including HIV/AIDS.

- WASH and nutrition

- Food Insecurity

- BMS Code

- COVID-19

- Gender roles related to nutrition

- Climate change and nutrition

Advocacy Topics and activities planning for the next 12 months

| Topic | What do we want? | How do we do? | Attended Organisations | Remark |
| --- | --- | --- | --- | --- |
| First 1000 Days of Life | SUN CSA Laos breastfeeding-friendly workplace. Encourage all organisations to have strong, supportive policy and practice for BF in the workplace. | - I support Breastfeeding video/campaign - Conduct a survey on workplace breastfeeding - Produce brochure – Best practice on workplace breastfeeding - SUN CSA Laos Workplace Breastfeeding Awards Survey | SUN CSA SEC, SUN CSA Members | In progress |
|  | Pregnancy – Advocate for giving birth at health facility | Advocacy with groups? On hospital birth. conducting ANC |  |  |
|  | Advocate in community for good practice during 0-6 month life. | Promote vaccination for infants and ANC visits etc in communities…. (publicity campaigns?) |  |  |
|  | Promote birth spacing | Publicity campaign for birth spacing? – (target public? Families?) |  |  |
|  | Public awareness of 1000 days steps | Public awareness campaign on 100 days stages. Social media? |  |  |
|  | BF room |  | WVIL |  |
|  | Understanding Need of disability Children on NUT | - Survey - Brochure | HI |  |
| Inclusion of vulnerable people, including ethnic minorities, PWDs, people living with illness, including HIV/AIDS. | Include people living with HIV/AIDS into the national Insurance system | - Propose to the Govt - Raising awareness on nutrition for people living with HIV/ADIS - ETC… | APL+ |  |
|  | Understand needs | - Survey on behavior and communication | QLA | Oct |
|  | Promote Inclusion success and failures | - Develop Case studies on inclusion in communities | APL+ | Nov-Dec - |
|  | Share information | - Dissemination of tools and laws | LDPA CPS, MHP | Jan-March |
|  | Understand needs | - Survey on behavior and communication | QLA | Oct |
| WASH and nutrition | ODF | - ODF Map on households using a proper toilet - Promote WASH Marketing with PNC - Social media promotion of ODF achievement and progress. (successes in communities; share case studies) | SUN CSA Members ARMI |  |
|  | Promote forest protection to maintain water sources. |  |  |  |
|  | Promote water filters? |  |  |  |
|  | Promote demand for ‘potable’ water in communities (CLTS?) | Share CLTS materials between organisations. Social media promotion of clean water source protection. |  |  |
|  | Promote handwashing in communities | - Share materials promoting soap handwashing between orgaisations. Develop ‘best practice materials? Post on SUN CSA website) - Case studies of handwashing success - Celebrate International handwashing day. Share activities via social media. | SRC |  |
|  | Raise awareness of best practice of waste disposal | - Share examples between organisations - Promote on Sun CSa social media and website |  |  |
| Food Insecurity | Raise awareness of food insecurity issues | - Dissemination of SUN CSA survey results - Social media sharing of results and needs of community (SUN CSA FB and org FB) - Case study videos of results of FS survey |  |  |
|  | Promote responses by all stakeholders to address food security issues |  |  |  |
|  | Promote home gardens | - Share materials and best practice (ie role models) between SUN CSA orgs – hangouts?; website - Case studies about successful home gardens; - Social media posts about how to make successful home gardens; ‘show your home garden competition’? |  |  |
|  | Promote food preservation | - Share best practice between members (hangouts; post on website) - Case study of success stories - Video instructions on making home gardens? Share between communities; social media… |  |  |
| BMS Code | BMS Decree has been approved | - Propose the topic to the Government | SCI, CARE, UNICEF | Done |
|  | Hotline for reporting the BMS Code Violation | - Disseminate the BMS Code/Violation | SUN CSA Members |  |
|  | No violation in health facilities | - BMS Code Key message - Disseminate the BMS Code/Violation |  |  |
|  | No violation in the shop/import companies | - BMS Code Key message - Disseminate the BMS Code/Violation |  |  |
| COVID-19 | Increased number of Lao people get vaccination | - Raising Awareness - Promote the campaign - Produce IEC materials - Support at the vaccination points/units - Mobile clinic – Vaccination at Village and School. - ETC… | SUN CSA Members |  |
|  | New normal/people living safely with COVID | - Material for Media (Video, poster…) | SUN CSA Members |  |
| Gender roles related to nutrition | GEDSI guideline is produced |  | SUN CSA Members | Done |
|  | Gender equality awareness in office and community |  | SRC |  |
|  | External Survey on Gender/leadership |  | SRC |  |
|  | Promote women role on breastfeeding |  | SRC |  |
|  | Promote women empowerment | Peer to peer learning Activity | SRC |  |
| Climate Chang and Nutrition | Recover after flooding and drought – providing seed, animal |  | Caritas |  |
|  | Disaster awareness - survey/report |  | Caritas |  |
|  | Forest protection |  | SNV |  |
|  | Build weir to maintain water during dry season |  | SRC |  |